## Slide 1: Integrated US SRF Program for FCC-ee
Matthias Liepe
Professor of Physics; Head Cornell SRF Group
Cornell University
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 1
For Program Partner Institutions

## Slide 2: Integrated US SRF Program for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 2
US Strategic Participation in the FCC-ee Nb SRF Development
Motivation / introduction
Proposed Scope
Proposed Timeline
US Rapid Development Program for Nb3Sn SRF Technology
Motivation / introduction
Proposed Scope
Proposed Timeline

## Slide 3: FCC-ee SRF Layout and Specifications
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 3
400 MHz 2-cell cavities: 10.6 MV/m, Q0~3×109 @ 4.5K
Or 600 MHz 2-cell cavities: 14 MV/m (: 20.5 MV/m), Q0~3×1010 @ 2K
800 MHz 6-cell cavities: 5-17 MV/m (: 20.5-23 MV/m), Q0~3×1010 @ 2K

## Slide 4: FCC-ee SRF Roadmap
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 4
Slide credit: Adopted from F. Gerigk, FCC Week 2026
Full power CM testing ~2034
CM production start ~2038
~8 years till full power CM test; ~ 12 years till start of CM production
Low power CM testing ~2031

## Slide 5: U.S. Superconducting RF R&D Leadership
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 5
High-Q0 SRF cavity process R&D
FCC-ee 800 MHz prototype cryomodule design at Fermilab
U.S. is a leader in SRF science and technology
  LCLS-II high-Q (nitrogen doping) and cryomodules (FNAL, TJNAF, SLAC, Cornell)
  PIP-II high-Q cavity and full system development (FNAL)
  EIC SRF (TJNAF, BNL)
  FRIB SRF (MSU)
  LHC crab cavity development (FNAL, TJNAF)
  SNS Energy Upgrade (TJNAF, SNS)
  General SRF R&D (GARD): high Q, high gradient, Nb3Sn…
U.S. is well positioned to take on SRF R&D leadership for FCC-ee
  800 MHz cavity and prototype cryomodule development (FNAL)
  High Q0 R&D (FNAL, TJNAF, ANL, Cornell)
  Breakthrough Nb3Sn R&D (Cornell, FNAL, TJNAF)
Beyond FCC-ee, continued SRF R&D highly relevant for other future accelerator projects, e.g., EIC, FRIB energy upgrade, industrial accelerators…
FCC-ee SRF R&D aligns well with the U.S. long-term priorities.
Continued focus on SRF R&D with sustained support and investment critical for future colliders and workforce development

## Slide 6: Integrated US SRF Program for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 6
Our vision:
Establish a nationally coordinated effort on SRF
  Like the U.S. LHC Accelerator Research Program(LARP) collaboration on LHC magnet development
Well-aligned with (updated) DOE GARD RF Roadmap => see Sam’s talk
Focused on high-impact for FCC-ee and the US accelerator program
Closely coordinated with CERN
Funded via US FCC-ee support and DOE GARD
Proposed US Institutional participation: ANL, Cornell, JLab, Fermilab,…

## Slide 7: Integrated US SRF Program for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 7
US Strategic Participation in the FCC-ee Nb SRF Development
Motivation / introduction
Proposed Scope
Proposed Timeline
US Rapid Development Program for Nb3Sn SRF Technology
Motivation / introduction
Proposed Scope
Proposed Timeline

## Slide 8: US Strategic Participation in the FCC-ee Nb SRF Development
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 8
CERN FCC-ee leadership wants the US to contribute in the area of SRF, and to ramp up our engagement as much as possible.
The HENP budget remains constrained due to the imperative to deliver on major commitments (HL-LHC, LBNF/DUNE, PIP-II).
US FCC-ee activity at this time must be scoped in this context.
Small, strategic program proposed here for US institutions.
Program carefully designed to align with CERN’s priorities.
Gives the US a chance to make meaningful contributions to ongoing FCC-ee accelerator efforts.
Program is aimed to show US commitment and position the US to play a significant role should CERN give the green light in 2028, all while maintaining a limited budget.

## Slide 9: FCC-ee Nb SRF Development Program
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 9
SRF system where CERN has sought outside contributions so far has been the 800 MHz cryomodules.
Through the INFRA-TECH 2026 European call, European institutions plan to build an 800 MHz FCC-ee cryomodule demonstrator.
  CERN, IJCLab, CEA, ESS, DESY, HZB
  Not realistic building a prototype module in the US at this time.
But: Opportunity to contribute to a European prototype cryomodule, leaning on US strengths in high-performance SRF.
  Makes the US an intellectual and technological partner in this development.
US partner institutions

## Slide 10: US Capability and Experience for FCC-ee Nb SRF Development
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 10
800 MHz modules: bulk niobium cavities requiring high Q at medium fields.
  FCC 800 MHz cavity performance goals are challenging but seem within reach of current advanced techniques with focused R&D.
US leadership and capability in high Q, high gradient cavities and cryomodules is highly relevant here:
  N-doping breakthrough development
  Low-T and mid-T heat treatment development
  Optimized EP development
  LCLS-II, LCLS-II HE, PIP-II
Image credit: Daniel Bafia

## Slide 11: Proposed Scope: Overview
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 11
Perform high Q process R&D at 800 MHz.
Transfer optimal processing steps to 800 MHz 6-cell cavities.
Treat and test 800 MHz cavities for prototype cryomodule
TBC: Weld helium tanks to prototype module cavities and retest.
TBC: Design of 800 MHz cavity frequency tuner and test.
Note: This 800 MHz high-Q Nb development is relevant for FCC SRF in the 600 – 800 MHz range.
Deliverable: 4 qualified, jacketed 6-cell 800 MHz cavities with tuners, plus 1 spare.
CERN FCC-ee leadership voiced strong support for this proposed US scope.

## Slide 12: Proposed Scope: Details
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 12
Perform high Q process R&D at 800 MHz:
Goal: Determine best treatment process at 800 MHz.
  Note: 800 MHz sits between the PIP-II (650 MHz) and LCLS-II (1300 MHz) frequencies.
Fabricate 3 to 4 single-cell 800 MHz cavities (in addition to those provided by CERN).
Conduct systematic single cell 800 MHz cavity treatment optimization.
  E.g., EP baseline, followed by mid-T at various temperatures.
  Cross-US-facility performance validation.
Process R&D primarily funded by GARD.

## Slide 13: Proposed Scope: Details (cont.)
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 13
Transfer optimal processing steps to 800 MHz 6-cell cavities.
Five 6-cell 800 MHz prototype cavities to be sent to the US from Europe for high Q and high gradient treatment.
Tooling and infrastructure preparations for 800 MHz cavities
Perform a limited number of treatment cycles to establish optimal steps.
Treat and test 800 MHz cavities for prototype cryomodule
Using optimized process, perform treatment of 4+1 cavities.
TBC: Weld helium tanks to prototype module cavities and retest.
Tanks provided by European partners
TBC: Design of 800 MHz cavity frequency tuner and test.
Use FNAL experience in cavity tuners to modify existing design to 800 MHz cavity and test with cavity.

## Slide 14: Timeline
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 14
Task | FY27 | FY28 | FY29 | FY30
800 MHz single-cell fabrication |  |  |  | 
800 MHz single-cell high Q process R&D |  |  |  | 
Tooling and infrastructure preparations |  |  |  | 
Receive 800 MHz 6-cell cavities from CERN |  |  |  | 
Treatment and vertical performance testing of 800 MHz 6-cell cavities |  |  |  | 
Helium tank welding and final test |  |  |  | 
Frequency tuner development |  |  |  | 
Send qualified, jacketed 6-cell 800 MHz cavities to CERN for module assembly |  |  |  | 
Cavity delivery in time for string and cavity assembly of 800 MHz cryomodule by European partners planned for CY 2030/31.
FCC-ee go/no-go decision

## Slide 15: Some Notes on Cost (for the proposed initial scope)
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 15
Smooth ramp up in funding assumed with limited funds before go/no-go decision
  Estimate: Initial ~$200k/year, ramping up to ~$500k+/year
  Detailed bottom-up budget estimate currently under development with partner institutions (ANL, Cornell, Jlab, Fermilab)
Costs will be augmented by synergistic efforts, including existing R&D efforts under GARD as well as internal lab funds.
  Indication of support and buy-in for participation in the FCC-ee program.
The program would leverage existing investments in treatment and testing facilities at labs and universities.

## Slide 16: Integrated US SRF Program for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 16
US Strategic Participation in the FCC-ee Nb SRF Development
Motivation / introduction
Proposed Scope
Proposed Timeline
US Rapid Development Program for Nb3Sn SRF Technology
Motivation / introduction
Proposed Scope
Proposed Timeline

## Slide 17: Nb3Sn Breakthrough
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 17
Nb3Sn is a transformative material option for SRF (Tc=18K vs 9.2K).
Nb3Sn SRF breakthrough achieved by US institutions, supported by DOE HEP, especially HEP GARD (Cornell, FNAL, JLab).
Key benefit: SRF operation at 4.5K instead of 2K with similar Q0.
  Factor of 3 to 4 times higher overall efficiency!

## Slide 18: Nb3Sn Benefits for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 18
Using 4.5K Nb3Sn in SRF systems offers 3 significant advantages compared to using Nb:
  Higher cryogenic efficiency, meaning that a smaller cryoplant can be used, reducing infrastructure costs.
  Smaller cryogenic plan requires less power, lowering operating costs.
  Cryogenic system at 4.5 K reduces operational risk.
Factor of ~3 reduction in carbon footprint for cryo!
Translates into cryoplant construction cost savings of several tens of $M and 10-year operating cost reduction of the order of $100M.

## Slide 19: Nb3Sn State of the Art Performance
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 19
Supercond. Sci. Technol. 34 (2021) 025007
Gradients 20+ MV/m on single-cell cavities, meeting FCC-ee needs
Q0 > 1010 at 4.5K
1.3 GHz
650 MHz
Supercond. Sci. Technol. 34 (2021) 025007

## Slide 20: Nb3Sn Field Potential Demonstration at Cornell
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 20
Reached ~400 mT (corresponding to ~100 MV/m) in short-pulse RF operation on a Nb3Sn coated sample, 2x Nb limit.
Highest RF magnetic field achieved on a superconductor
Quench at ~370 mT!

## Slide 21: Towards Applications: Practical Nb3Sn Cavities
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 21
>15 MV/m with Q0~1010 at 4.4K on accelerator structures!
=> Becoming an option for accelerator projects!
4.4 K Q0 > 9x109 at quench
Fermilab: 9-cell 1.3 GHz cavities
CEBAF-style quarter module using Nb3Sn 5-cell cavities

## Slide 22: US Rapid Development Program for Nb3Sn SRF Technology
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 22
So far: Individual U.S. Nb3Sn SRF research programs
  Coating process developments and breakthrough performance demonstrations, with 1-cell cavity performance approaching FCC-ee needs
  More development efforts are needed now to demonstrate performance in a cryomodule.
  If higher Q0 values are obtained in those demonstrations, the Nb3Sn benefits will be similarly improved.
Now: Need a coordinated effort involving all key US players in this development to fully develop Nb3Sn technology at the cryomodule level and to demonstrate project readiness.

## Slide 23: US Rapid Development Program for Nb3Sn SRF Technology
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 23
A US Nb3Sn initiative could enable Nb3Sn SRF to be a part of the baseline for FCC-ee with substantial benefits for infrastructure and cryogenic energy savings.
Benefits reach far beyond FCC-ee:
  Lower construction and operating costs for SRF driven lights sources, neutron sources, muon collider…. Revolution in SRF technology
  Nb3Sn enabling technology for taking SRF into industrial settings
    Conduction-cooled, cryocooler-based Nb3Sn SRF
    Nb3Sn highly beneficial and sought-after technology for large industrial accelerators, for example for semiconductor lithography and subcritical reactors.
  Program would cement U.S. leadership in (Nb3Sn) SRF technology with huge benefits to all further SRF driven accelerators.

## Slide 24: Nb3Sn Program Specifics
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 24
3 major program parts:
  Enabling Nb3Sn R&D
    Coating optimization (at FCC frequencies)
    Transfer to multi-cell cavities (at FCC frequencies)
    Nb3Sn cavity technology R&D (handling, tuning, tank welding…)
  Nb3Sn Coating Scale-Up and Industrialization
    Dedicated Nb3Sn coating facility development and deployment
    Multiple coating facilities for cross-checking between institutions (as was done for N-doping development for LCLS-II)
    Technology transfer and licensing to industry

## Slide 25: Nb3Sn Program Specifics
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 25
  Prototype Cryomodules
    Approach: Program sized to providing data needed to support baseline change of FCC-ee from Nb SRF to Nb3Sn SRF
    FCC cavity coating and performance testing at multiple institutions
      20 cavities at given frequency to demonstrate performance yield
      Goal: Consistent performance demonstration meeting FCC specs
    Nb3Sn prototype cryomodue(s) design, production, assembly and test
      Goal: Lower frequency (600/650 MHz) prototype fully tested by CERN’s ~2034 target
      Goal: Higher frequency (800/1300 MHz) prototype fully tested in time for ttbar upgrade

## Slide 26: 12-Year Timeline
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 26
Area | Tasks | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12
Enabling R&D |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Substrate optimization and specification R&D |  |  |  |  |  |  |  |  |  |  |  | 
 | Single cell 600 MHz R&D |  |  |  |  |  |  |  |  |  |  |  | 
 | Single cell 800 MHz R&D |  |  |  |  |  |  |  |  |  |  |  | 
 | Multicell 600 MHz R&D |  |  |  |  |  |  |  |  |  |  |  | 
 | Multicell 800 MHz R&D |  |  |  |  |  |  |  |  |  |  |  | 
 | Tuning/handling development |  |  |  |  |  |  |  |  |  |  |  | 
 | Helium tank integration development |  |  |  |  |  |  |  |  |  |  |  | 
Nb3Sn Coating Scale-Up and Industrialization |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Design furnace |  |  |  |  |  |  |  |  |  |  |  | 
 | Set up facility for prototype furnace – utilities, space, etc. |  |  |  |  |  |  |  |  |  |  |  | 
 | Deploy, commission, and debug first furnace |  |  |  |  |  |  |  |  |  |  |  | 
 | Set up facilities for subsequent furnaces |  |  |  |  |  |  |  |  |  |  |  | 
 | Build subsequent furnaces (2) |  |  |  |  |  |  |  |  |  |  |  | 
 | Technology transfer & licensing to industry |  |  |  |  |  |  |  |  |  |  |  | 
Color scheme | 
 | 600/650 MHz
 | 800/1300 MHz
 | Generic

## Slide 27: 12-Year Timeline (Cont.)
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 27
Area | Tasks | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12
Prototype Cryomodule |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cavity production (20 of each frequency) |  |  |  |  |  |  |  |  |  |  |  | 
 | Cavity coating at multiple US facilities |  |  |  |  |  |  |  |  |  |  |  | 
 | Consistent performance demonstration |  |  |  |  |  |  |  |  |  |  |  | 
 | Alternative 1 (new 4K CM Design) |  |  |  |  |  |  |  |  |  |  |  | 
 | New 4K cryomodule design |  |  |  |  |  |  |  |  |  |  |  | 
 | Horizontal tests for design verification |  |  |  |  |  |  |  |  |  |  |  | 
 | Full scale prototype 4 K cryomodule production |  |  |  |  |  |  |  |  |  |  |  | 
 | Full scale prototype 4 K cryomodule test |  |  |  |  |  |  |  |  |  |  |  | 
 | Alternative 2 (Usage of existing PIP-II "650MHz" Design) |  |  |  |  |  |  |  |  |  |  |  | 
 | "650 MHz" cryomodule Procurement |  |  |  |  |  |  |  |  |  |  |  | 
 | "650 MHz" cryomodule Production |  |  |  |  |  |  |  |  |  |  |  | 
 | "650 MHz "cryomodule Test |  |  |  |  |  |  |  |  |  |  |  | 
 | Transportation testing |  |  |  |  |  |  |  |  |  |  |  | 
 | Microphonics studies as needed |  |  |  |  |  |  |  |  |  |  |  | 
 | High current beam test at Cornell |  |  |  |  |  |  |  |  |  |  |  | 
 | Integrated cryomodule test at CERN |  |  |  |  |  |  |  |  |  |  |  | 
Color scheme | 
 | 600/650 MHz
 | 800/1300 MHz
Meets CERN timeline for (low-power) CM testing in 2031

## Slide 28: Some Notes on Cost
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 28
Major multi-institution U.S. initiative, similar to magnet program of the the U.S. LHC Accelerator Research Program (LARP) collaboration (~$6M/year in 2000 era dollars).
Working on putting together detailed budget estimate, including alternative options / budget scenarios.
  (a) Rapid program to impact FCC-ee baseline covering two RF frequencies or (b) single-frequency timeline that leads to prototype to impact ttbar upgrade.
  (a) New 4.5K Nb3Sn FCC cryomodule design or (b) use of existing PIP-II module design.
  Flexible to adjust to final FCC-ee frequency choice.

## Slide 29: Integrated US SRF Program for FCC-ee
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 29
US Strategic Participation in the FCC-ee Nb SRF Development
Motivation / introduction
Proposed Scope
Proposed Timeline
US Rapid Development Program for Nb3Sn SRF Technology
Motivation / introduction
Proposed Scope
Proposed Timeline

## Slide 30: Key Takeaways
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 30
Exciting opportunities for the US for leadership in high-impact SRF technology development
  Opportunity to contribute to a European prototype cryomodule, leaning on US strengths in high-performance SRF
    Shows US commitment and positions the US to play a significant role should CERN give the green light in 2028, all while maintaining a limited budget.
  US Rapid Integrated Development Program for Nb3Sn SRF Technology
    Major initiative that would be transformative for future SRF accelerators, including FCC-ee

## Slide 31: Thank you for your attention!
M. Liepe, Cornell University Fourth US FCC meeting, 2026, September 10 Slide 31