## Slide 1
QCM Accelerator Update
10 February 2026
Galen Aymar

## Slide 2: QCM Overview
Original goal: demonstrator for C3
Additional goal: provide QCM to ESRF for their linac upgrade
  The full C3 design works for ESRF, but ESRF has less stringent requirements
  ESRF’s schedule is to receive this QCM in June 2027
VESSEL
ACCELERATOR STRUCTURE
QUADRUPOLE
RAFT
INSTALLATION HARDWARE
MOUNTS

## Slide 3: Proposed Schedule
Mechanical assembly of the QCM to start by Nov 2026, allowing testing before shipment to ESRF by June 2027

## Slide 4: Final RF Geometry
1-m structure: 40-cell with damping slots
Features
  40 cells with pair wise side to side distributed coupling
  Cell Balancing features
  4 damping slots extending to the beam center line (4 part open cells and iris)
  Structures to be spaced so that cell center to center distance is (N+.5)*26.242 at operating temperature
0.3mm
0.1mm
42.020 mm
21.010 mm
Damping slot
0.25 mm rounding
R2mm
Waveguide corner rounding

## Slide 5: FEA: Pool Boiling Temperatures & Thermal Expansion
Case with no cooling at the tuner surfaces indicates inside temperatures at approximately 4° above the LN bulk temperature.
As this is “well below” the film transition temperature of ~10°, no modification of the tuning features is thought essential.
Distortion from RF heating and 3 atm pressure (Tref is cold)
Case without any tuner surface heat transfer
Displacement of less than .5µm is acceptable
Some tuning offsets to compensate for end effects may be incorporated.

## Slide 6: Mechanical Features - External
Part handling feature for machining – TBD by vendor
Mounts for Rasnik or laser nests
Braze clamping pads
Cell tuners
Thru-holes for bolt clamping at braze
Mounts for struts to support raft
Alignment surfaces to be machined in one pass at the final step, checked/recorded

## Slide 7: Mechanical Features - Internal
Braze surfaces
Waveguide feed
Damping slots
Cells and irises
Internal radii around cells at split face
Riris
Rcell
Rdamping slot

## Slide 8: Braze Steps and Features
3 critical “perimeter” joints (2 vacuum, 1 mechanical)
During braze, the braze joints are held by external clamps and compression bolts.
At assembly, alignment is achieved with a pin and slot arrangement, using stainless steel inserts to prevent deformation of the hole and slot (Exterior flat surfaces may also be used)

## Slide 9: Procurement
17 potential vendors have been contacted about manufacturing the machined copper quadrants.
9 have expressed a strong interest in the project.
A SLAC-internal procurement requisition is currently being routed for approvals and is expected to be posted to sam.gov for bidding in the coming weeks.

## Slide 10: Mechanical Features – Alignment and Fiducials
C3 requires: Very high precision structures, quad on piezo 5 DOF stage, raft with 5 DOF stepper adjustment, Rasnik alignment feedback, beam position monitor.
ESRF needs: Precision alignment of the structures in the QCM to the machine coordinates (beam tunnel/mating components) and a means of verification/adjustment.
Option 1:
  CMM alignment of accelerators to laser nests on the raft
  Laser alignment of laser nests on the raft to laser nests on the QCM external face
  Survey QCM external lasers nests for alignment at ESRF
Option 2:
  CMM alignment of beam tunnel to laser nests on the structure (visible through view ports)
  Calibration of laser nests on structure through windows and LN2 (discuss with SLAC/ESRF alignment teams)
  Survey laser nests on structure to do alignment at ESRF

## Slide 11: QCM Accelerator Installation Fixture
Entire structure (raft with two accelerator structures) is installed into the QCM from one end riding on vertically adjustable shafts.