## Slide 1
COLD update
30th April 2026
S.Liuzzo, on behalf of the EBS COLD project team and the international collaboration: SLAC, INFN, CERN, PSI, CORNELL

## Slide 2: C-band Linac ~150-300 MeV pre-injector: OBJECTIVES
Accelerating Gradient
Breakdowns (10-7 /pulse /meter).
Acceleration in presence of a breakdown
Dark currents
Compact
Reliable, maintainable
alignment
Possible lower temperature reach
(need dedicated structure design)
Beam position
Ytterbium laser
Radiation safety
RF deflector
Dipole
Radiation safety
Beam charge
steerer
3xQuadrupole
Vacuum valve
PC
50MW
4ms
4Hz
35MW
WP1
WP10
WP3
WP2
WP2
WP2
WP1
WP8
WP1
Low Level RF
S-band
C-band
WP9
Beam charge
Radiation safety
Radiation safety
Radiation safety
Cryomodule 3.3m
WP10
Beam position
Cryomodule 2.7m
Vacuum valve
Beam position
Beam position
Quadrupole
Beam energy
7MeV
150MeV
300MeV
steerer
Beam charge
Vacuum valve
ALIGNMENT
PULSE COMPRESSION
GUN
Solenoid
CRYOMODULE
BEAM PROPERTIES
HIGH CHARGE
Low emittance
HIGH GRADIENT
RF CONTROL
Vacuum valves
Vacuum valves
OBJECTIVES
Diagnostics
RF
Magnets
Infrastructure
Safety
Laser
Legend
Control
Control system
LONG PULSE
WP7
WP9
WP7
WP3
WP4
WP1
WP4
WP1
WP1
Hardware interlocks
Safety interlocks
Vacuum valves
Shot – shot reproducibility
Energy, Emittance
Bunch length, charge

## Slide 3: Timeline for the COLD projecT
Date | Instrument added to the installation | Beam achievements | project
2026-Aug SD | Grounding, holes in tunnel wall, cable trays |  | Phase 0
2026-Oct SD | Handling, air extraction (LN2 leaks), water (temp) |  | Phase 0
2026-Dec SD | ModS4- RF-unit (SAT) |  | Phase 0
2027-May SD | First C-band RF-unit |  | Phase 0
2027-Aug SD | First C-band Acc. Struct. |  | Phase 0
2028-May SD | Infrastructures installation |  | Phase 1
2028-May SD | Diagnostics and beam dump |  | Phase 1
2029-Jan SD | S-band photo-gun + laser | 7MeV photogun beam | Phase 1
2029-May SD | Beam in Acc. Struct. | 150MeV beam (expected 150) | Phase 1
2030-May SD | RF deflector | 2ps bunch length | Phase 1
2029-Dec SD | Second C-band RF-unit (if needed) and new injector design acc.struct |  | Phase 2*
2030-Sep |  | 300MeV beam (expected 300) | Phase 2*
2031-Aug SD | TL1upgrade and inject in booster | 300MeV beam to booster | Phase 3*
* No planning or budget at the time being
Delivery Jan 2026
SAFETY authorization for Phase 0, 1, 2, 3
EIC grant proposal for Phase 0, 1, 2
Budget and planning for Phase 0, 1
CFT April 2026
new
new

## Slide 4: Layout in LINAC bunker

## Slide 5: WP-01 RF
Definition of the RF power distribution, pulse compression studies, etc..
S-Band RF-unit purchased for photo-gun.
Fully compatible (identical) to the new RF-Units purchased for the present linac refurbishment.
In case COLD project is delayed, this equipment can be used for USM operation.
First component of COLD project purchased in 2025
C-band RF unit to be purchased in 2026 (needed July 2027)
Used Unit from PSI
New unit (Call for Tender)
Possibility of Buy-back proposed by Scandinova
 CFT for new RF-unit + buy back option request.
Second component of COLD project CFT lunched in April 2026
new

## Slide 6
Ideal solution: Pharos 2H-4H from Light Conversion
  Diode pumped Yb-crystal laser (l = 1030 nm) with integrated 4th harmonics generation:
This laser is already used as UV-photon source for at
DESY (S-band photoinjector at SINBAD-ARES)
CERN CLEAR/CTF2 photoinjector
Photoinjector of CXFEL (Arizona State University)
Positive feedbacks on performance and service (beam quality, stability, long term reliability,…)
827 cm
492 cm
25 cm
190 fs
WP-02 diagnostics: Pharos 2H-4H from Light Conversion
= 257 nm
E = 100 - 200 uJ / pulse depends on model
Single shot – 100kHz
Synchronisation to SSRF/4 (88 MHz)
Compact
150 MeV beam dump (ThomX) designed by P.Berkvens.
Will design for COLD a similar one for 350MeV. Works as Faraday cup as well.

## Slide 7: WP-05 infrastructure
Water cooling
2-300 kEuro
High quality
High reliability
Possible impact on Facility operation
3-400 kEuro
High Quality
Independent from main facility
Additional maintenance needed
Limited to 2 RF-units.
SELECTED
Potential for future use, Phase 3
new

## Slide 8: WP-06 Operation
Gun
Bunch
C3_1
Gun
Laser
Mod S_4
Mod C1
C3_2
Diag &Optics
PC
325 MeV
325 MeV
Scandinova
Scandinova
Scandinova
Section 2
Section1
Mod S2
Mod S 1
Mod S0
Mod S3
Overhead crane ?  NO
Installation procedure: what enters and when.
Space for storage and handling solutions
Space availability in the PINJ modulator hall
Door separations
The modulator hall is getting more and more free to make space for COLD project
2026 August and October Shutdowns
new

## Slide 9: WP-07 Controls
We could consider the preparation of a digital twin based on RF-Track simulations as the one of the EBS-SR to start creation of Device Servers and applications for control of COLD.
PRESENT LINAC
Interlocks: several WP involved RF, safety, operation, control, etc…
new

## Slide 10: WP-08 Alignment
Measurement of the earth embankment that covers the linac tunnel for SAFETY approval request to ASNR.
Linac
Modulators
hall
grass-covered earth mound
COMPLETED on 24th September 2025
March 2026  3D Laser Survey of the Tunnel interior. Next shutdown (May) installation of HLS in linac tunnel.
new

## Slide 11: WP-09 SAFETY
The procedure to obtain L'Autorité de sûreté nucléaire et de radioprotection (ASNR) approval requires drawings, simulations and a CDR document.
~2 years to obtain permission for beam. We are on schedule and started preparing the documentation.
6GeV Linac Injectors upgrade project is the ultimate justification for ASNR to approve COLD project
ASNR approval deadlines:
COLD authorization starts right after Linac Refurbishment
Prepare  6month  Submit  1 year  Obtain (accelerators)
Submit  6 month (or less)  Obtain (klystrons)
1st Dec 2025: Prepare Drawings and beam information for Linac refurbishment (DONE)
Submit authorization for S-band RF unit (Klystron) (DONE, BUT NOT OBTAINED YET)
1st July 2026: Submit authorization request to use RI structure as spare (sent)
Obtain authorization for S-BAND RF units (klystron)
2nd July 2026: Prepare Drawings and beam information for Phase 1-2-3-… Linac parameters 1000 part 6D beam at linac end
Submit authorization for C-band RF unit (Klystron) Phase 0
1st Jan. 2027: Submit authorization request for Phase 1-2-3
Obtain Authorization for C-band RF unit Phase 0
1st July 2027 : Obtain Authorization for linac refurbishement beam
1st Jan. 2028 : Obtain Authorization for beam and RF Phase 1-2-3-…
new

## Slide 12: WP-10 Magnets and Power supplies
More correctors needed (2) and quadrupole to be installed on mover or with integrated H/V correction coils
Included in the list of participants to the project also Power Supply Group.
2 H/V correctors (similar to the ones of TL1), 2028
1 quadrupole (similar to the ones of TL1), July 2027
1 dipole (similar to the ones of TL1), 2028
1 solenoid (the PS will likely be part of the photo-gun purchase), 2028
Low Power consumption, AIR COOLED magnets.
new

## Slide 13: Collaboration working on emittance simulations differences RF-Track - ASTRA
Wei-Hou Tan, SLAC
G.J.Silvi, INFN
SITF
SITF
200ps
SITF
700pC
In ASTRA simulations, emittance is ~ 1 mm mrad

## Slide 14: RF-Track simulations
Final 4d emittance at linac start = 1.05 mm.mrad; at linac end 1.08 mm.mrad
A.Latina, CERN
1) interpolate 1D fieldmaps on a regular 1D mesh, 2) smoothing function similar to that used in Astra 3) fund a better working point using Bayesian optimisation in Xopt to get a small emittance at the entrance of the first linac structure using the gun phase and the solenoid field as degrees of freedom.
sr = 0.3 mm (gaussian)
st = 2.79ps (gaussian)
0.289795 T
Different optimal parameters.
0.823 m gunlinac
new

## Slide 15: WP-12 Timing
This WP is recently added to the project.
2998.8 MHz
5712.0MHz
142.8MHz
X 21
X 40
GUN
Accelerating structures
352.372174 MHz
Storage Ring
Wait for coincidence within a given limit.
NO
NO
NO
GO!
EU S-BAND
C-BAND
COMPATIBLE WITH PRESENT LINAC
MAX-IV propose their solution to generate the S-band and C-band signals from the laser.

## Slide 16: Planning, HR and WP organization @ ESRF
Including resources and following an almost flat financial profile is set up with the available tools (excel mainly).
~200 tasks
30 people
WP-01 RF
WP-02 Diagnostics and Laser
WP-03 Vacuum
WP-04 Mechanical Engineering
WP-05 Infrastructure
WP-06 Operation
WP-07 Controls
WP-08 Alignment
WP-09 Safety
WP-10 magnets
and power supplies
WP-11 beam dynamics
WP-12 Timing
A.D’Elia
F.Ewald
H.Pedroso Marques
T. Brochard
Y. Gouez
J.-L. Revol
R. Bourtembourg
C. Gonzalez Torres
P.Colomp
C. Benabderrahmane
P. Falaise
S.M.Liuzzo*
Not. Available
Q.Qin, P.Borowiec, S.White, J.-L.Revol
Management:
Human resources:
3-years contract for cryomodule design
3 years contract for diagnostics/laser
3 years contract for RF accelerating structures design for Phase 2 (could be a PhD)
3 years contract for mechanical engineering
Resources for Safety and Infrastructure (to be defined)
Needed:
Hiring:
1 COD selection in progress for LLRF (3 years)
1 PhD open for Beam Dynamics (6GeV linac)
1 COD to be opened for high power RF (3 years)
* project coordination
new

## Slide 17: BUDGET
S-band RF unit
C-band RF unit,
infrastructure
Diagnostics, waveguides, laser, acc. structures
Photo gun,
Pulse compressor
RF deflector
Financial profile and budget codes are set up
High power RF measurements
Beam
infra
RF
DIAG
BUDGET EVOLUTION:
April 2025: ~5M€
June 2025: ~6.0M€
October 2025: ~6.5M€
+ Infrastructure, RF-deflector
+ Detailed inputs from all WPs
+ updated costs
6.5MEuros total to reach Phase 1:
- 250 k€ refilling QCM with 300l dewars
- 250 k€ if we can leave without RF-deflector
+100K

## Slide 18: European commission EIC grant application
We are applying to EIC Pathfinder Open
Deadline for submission 12th May 2026 (open 5th February ‘26)
High risk - high gain project
Bring technology to no more than TRL4 (Technology validated in lab)
22 pages to be filled in: Excellence, Impact ( applications other than basic science, could be medicine, industry), Quality, budget.
Lump sum payments, budget pre-approved, advance payments and residual at WP finalization.
2.1% success rate last year (likely will need to resubmit next year)
4-5 labs, 5-7 WPs, SLAC can be an associated partner
For people-travel-consumables not for hardware
4 millions over 60 months
ESRF
INFN
CERN
SCANDINOVA
Instrumentation Technologies
SLAC (Associated, no budget)
Submission
7th May 2026

## Slide 19: rough draft timeline f0r EIC proposal
Tasks and Budget FROZEN.
Only editing phase.
Lump sum = payment at each WP conclusion  WP must be staggered
T0 could be October 2026
planning linked to COLD project master planning
BENKEI company hired for 2x project review. Last review will take place in 24th April.
Could finance 4 additional HR for: Cryogenics, Laser, RF, Mechanical Engineering (phase 2 cryomodule)
2% success rate in 2025
Includes: Alignment dummy cryomodule
Phase 2 cryomodule
T0=2026
Tend=2031
3 person/month spent to prepare this proposal

## Slide 20: Review Panel 21st April
SLAC partners
INFN, CORNELL
PSI
Partners, from remote
CERN partners
Panel members: CERN, DESY, MAXIV, CEA

## Slide 21: Feedback from Review Panel 21st April  aVAILABLE to MAC
Key recommendations (highlights):
Keep open for alternative 6GeV linac solutions (PWA, X-band, etc..)
Avoid placing too much effort on emittance optimization, no top-hat laser distribution
The development of a dummy cryomodule to test different systems to control the alignment at cold is essential for the project.
Establish strong partnerships with other laboratories that have that expertise. A key question that also has to be addressed is continued support and resources from the US partner lab.
Having a plan B for the delivery of the SLAC cryomodule should be secured in case funding changes occur for the US funded program, or in case of technical issues with the proposed four-quadrant assembly.
Properly vet the phase 0&1 project to ensure that the full budget is allocated.
Ensure that COLD diagnostics are capable of accurately measuring and characterizing the potentially shorter bunches then design (to control charge per bunch)
Explore energy tuning through adjustment of the pulse compressor fill timing
The proposed RF deflector for bunch length measurements seems excessive for the storage ring injection application. A simpler diagnostic setup based on a bending magnet and screen should be sufficient to characterize the longitudinal properties of beam.

## Slide 22: Many thanks for your attention
S.Liuzzo on behalf of the COLD project team:
A.D’Elia, P.Borowiec, V.Serriere, M.Dubrulle, M.Morati, S.White, F. Ewald, N.Benoist, K.Scheidt, B.Roche, C.Benabderrahmane, G. Le Bec, R.Bourtenbourg, J.-L. Pons, D. Martin, B. Pelissier, L.Eybert, T.Brochard, C.Maccarrone, J.-L. Revol, B.Joly, Y.Gouez, H. Pedroso Marques, P.Colomp, A.Dely, F.Falaise, David Frichet, Q.Qin
International collaborators
E.Nanni, A.Dhar, W.-H. Tan, G.Aymar (SLAC),
A.Latina (CERN),
D.Alesini, F.Cardelli, A.Giribono, C.Vaccarezza, G.Silvi (INFN-LNF),
M.Andorf, J.Maxson (Cornell),
P.Craievich, R.Zennaro (PSI)
6GeV Linac injector
Thank you for your attention!